## Overview
Beauty Guild Portal - UAT Test Pack
Purpose | Journey-based customer UAT for visible Beauty Guild portal, address lookup and Stripe test-payment flows.
Environment | Catalyst Development / Stripe test mode
How to use | Run each journey in the portal, record Actual Result, select Pass/Fail/Blocked and attach evidence.
Test data | Use dedicated test members. Never use live payment cards or production credentials.
Scope | Validate only portal actions and visible outcomes. Back-office checks are completed separately by the implementation team.
Journey | Test cases
01 Registration | 3
02 Login Dashboard | 3
03 Membership | 3
04 New Accreditation | 5
05 Address Map | 3
06 Course Selection | 3
07 Summary Submission | 4
08 Stripe Payment | 4
09 Awaiting Payment | 3
10 Qualifications | 4
11 School Portal | 5
12 Logout Return | 3

## 01 Registration
Test Case ID | Objective | Preconditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Evidence / Notes
REG-001 | Create a new member account | New email available. | Register with name/email and follow activation email. | Catalyst user is created and activation email is received. |  | Not Started
REG-002 | Validate required fields | Registration page open. | Submit with required fields empty. | Missing fields are identified and no incomplete user is created. |  | Not Started
REG-003 | Prevent duplicate registration | Email already has an account. | Register using the existing email. | Clear error appears and no duplicate user is created. |  | Not Started

## 02 Login Dashboard
Test Case ID | Objective | Preconditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Evidence / Notes
LOG-001 | Valid login | Activated user exists. | Enter valid credentials and submit. | User authenticates once and lands on Dashboard without a loop. |  | Not Started
LOG-002 | Invalid login | Login page open. | Enter incorrect password. | Clear error appears and user remains on login page. |  | Not Started
LOG-003 | Portal navigation | User is logged in. | Open Dashboard, Membership, GTi Courses, Accreditation and Insurance. | Items are clickable and active navigation is clear. |  | Not Started

## 03 Membership
Test Case ID | Objective | Preconditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Evidence / Notes
MEM-001 | Show active membership | Test member has a current membership and future expiry date. | Open Membership. | Membership type, Current status and expiry date display. |  | Not Started
MEM-002 | No active membership | Test member has no current membership. | Start an accreditation and reach Summary. | Associate Membership is shown as a separate price line. |  | Not Started
MEM-003 | Active member pricing | Test member has a current membership. | View accreditation Summary. | Only the standard accreditation total is included. |  | Not Started

## 04 New Accreditation
Test Case ID | Objective | Preconditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Evidence / Notes
ACC-001 | Start application | A test member is logged in. | Open Accreditation and select new application. | Wizard opens at Your details. |  | Not Started
ACC-002 | Required centre name | School Details is open. | Leave School Name blank and continue. | Continue remains unavailable until School Name is entered. |  | Not Started
ACC-003 | Prefill member data | Test member has existing contact and correspondence details. | Open Your details and Address. | Available member details prefill and remain editable. |  | Not Started
ACC-004 | Complete wizard | Required test information is available. | Complete all application steps. | Each step validates and progress works responsively. |  | Not Started
ACC-005 | Require tutor count | Tutors step is open. | Answer Yes to other tutors, confirm qualifications, and leave tutor count empty. | Inline guidance appears and continuation is blocked until a positive number is entered. |  | Not Started

## 05 Address Map
Test Case ID | Objective | Preconditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Evidence / Notes
ADR-001 | Postcode lookup | Loqate configured. | Enter UK postcode and select result. | Address fields populate. |  | Not Started
ADR-002 | Manual address | Address step open. | Use manual entry and complete fields. | User can continue and values persist. |  | Not Started
ADR-003 | Geocode marker | Valid address entered. | Open map step. | Map loads with marker at resolved location. |  | Not Started

## 06 Course Selection
Test Case ID | Objective | Preconditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Evidence / Notes
CRS-001 | Eligible courses | Test environment includes active GTI and ineligible courses. | Open Available accreditation courses. | Only eligible active GTI courses display. |  | Not Started
CRS-002 | Treatment groups | Eligible courses have treatment groups. | Review and expand course groups. | Courses are grouped by treatment group and easy to scan. |  | Not Started
CRS-003 | Course selection | Courses display. | Select several, deselect one, return to the step. | Selections persist accurately. |  | Not Started

## 07 Summary Submission
Test Case ID | Objective | Preconditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Evidence / Notes
SUB-001 | Review summary | Required steps complete. | Inspect Summary sections. | Details, courses and the customer-visible total match the information entered. |  | Not Started
SUB-002 | Accept terms and submit | Terms unchecked. | Try Pay Now; accept terms; select Pay Now. | Payment is blocked until acceptance, then checkout begins once. |  | Not Started
SUB-003 | Visible application status | Application has been submitted but not paid. | Return to Accreditation. | The application appears once under Payment required and View summary opens it. |  | Not Started
SUB-004 | Prevent duplicate submission | The first request may be delayed. | Select Pay Now once and wait for a result. | The button shows progress and only one visible application remains available. |  | Not Started

## 08 Stripe Payment
Test Case ID | Objective | Preconditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Evidence / Notes
PAY-001 | Open Checkout | An unpaid test application and Stripe test pricing are available. | Select Pay Now. | Stripe test Checkout opens with the same amount shown on Summary. |  | Not Started
PAY-002 | Verify pricing | Use one current member and one non-member test account. | Compare each Summary total with Stripe Checkout. | Current-member and membership-inclusive totals match on both screens. |  | Not Started
PAY-003 | Successful payment | Stripe test Checkout is open. | Use a Stripe test card and complete payment. | The user returns to the portal and the application no longer asks for a second payment after processing. |  | Not Started
PAY-004 | Cancel and retry | Stripe test Checkout is open. | Cancel, return to Accreditation and select Pay Now again. | The same application remains available and checkout can be reopened without a duplicate application. |  | Not Started

## 09 Awaiting Payment
Test Case ID | Objective | Preconditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Evidence / Notes
AWP-001 | Show awaiting payment | A test application is awaiting payment. | Open Accreditation. | Application appears once under Payment required. |  | Not Started
AWP-002 | Open summary | Awaiting application is listed. | Click the application or View summary. | The existing application opens at Summary while earlier steps remain unavailable. |  | Not Started
AWP-003 | Reuse payment route | Awaiting application exists. | Select Pay Now and wait; return and retry if required. | The existing checkout route or application is reused and the button shows progress. |  | Not Started

## 10 Qualifications
Test Case ID | Objective | Preconditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Evidence / Notes
QUA-001 | Add first qualification | A submitted accreditation is available in the portal. | Add name, month/year, centre, delivery and assessment; save. | A success message appears and the qualification is listed as Pending review. |  | Not Started
QUA-002 | Validate completion date | Qualification form is open. | Leave month/year incomplete. | Save remains unavailable until a valid month and four-digit year are supplied. |  | Not Started
QUA-003 | Add multiple qualifications | First qualification is listed. | Add a second qualification. | Both qualifications remain listed and Add qualification remains available. |  | Not Started
QUA-004 | Show processing status | Application has no qualifications. | Save the first qualification and return to Accreditation. | The application visibly shows Qualifications received or an equivalent processing state. |  | Not Started

## 11 School Portal
Test Case ID | Objective | Preconditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Evidence / Notes
SCH-001 | Open accredited school | A test member has one accredited centre. | Open Accreditation and select the centre. | Workspace shows the selected centre name, customer-friendly status and expiry. |  | Not Started
SCH-002 | Navigate school sections | School workspace is open. | Use Profile, Courses, Venues, Tutors and Qualifications. | Sections open and the active section is clear. |  | Not Started
SCH-003 | Manage multiple schools | Test member has two verified centres linked to separate accreditation records. | Return to Accreditation and open each centre in turn. | Centres list vertically and each workspace shows only the selected centre data. |  | Not Started
SCH-004 | Add a course | School workspace is open for an accredited centre. | Open Courses and review the Add course section below the accredited courses table. | Other available GTi courses are listed with a Get in touch action, without any duplicate top-level tab. |  | Not Started
SCH-005 | Responsive workspace | School workspace is open. | Narrow the browser window (or view on a mobile device) on Courses, Venues, Tutors and Qualifications. | Page content stays within the screen width with no horizontal page scrolling; wide tables scroll only within their own panel. |  | Not Started

## 12 Logout Return
Test Case ID | Objective | Preconditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Evidence / Notes
OUT-001 | Log out | User logged in. | Select logout. | Session clears and login page appears. |  | Not Started
OUT-002 | Prevent silent re-entry | User just logged out. | Refresh or use browser back. | User is not silently authenticated. |  | Not Started
OUT-003 | Log back in | User logged out with valid credentials. | Log in again. | User lands on Dashboard. |  | Not Started